## Gantt Chart Template
Year 12 Software Engineering – Gantt Chart Template
Task | Description | Duration | Dependencies
A | gather requirements from the medical centre | 1 week | none
B | system specifications | 1 | a
C | user interface prototypes | 2 | b |  | Legend: Path, Parallel track, Deployment
D | database structure | 1 | b
E | frontend booking system | 3 | c
F | backend and authentication system | 3 | d
G | frontend and backend systems | 1 | e. f
H | testing and debugging | 2 | g
I | deploy the system and train staff | 1 | h
Task | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
A | bar: deploy the system and train staff Week 1
B | bar: 1 Week 2
C | bar: h Week 3 to h Week 4
D | bar: h Week 3
E | bar: h Week 5 to h Week 7
F | bar: h Week 4 to h Week 6
G
H | bar: h Week 8
I | bar: h Week 9 to h Week 10