## Gantt Chart
Meeting Room Booking System (MRBS) – Project Schedule & Task Allocation (Gantt Chart)
Section 2.1 Project Management Software Engineering Year 12 Assessment Task 2
May | [16 empty] | June | [9 empty] | Legend:
15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Stage 1 Identifying & Defining
◆ | [26 empty] | Stage 2 Research & Planning
Stage 3 Producing & Implementing
Stage 4 Testing & Evaluating
◆ Milestone / Client Meeting / Submission
◆
◆

## Activity List
Meeting Room Booking System (MRBS) Project Schedule & Task Allocation (Activity List)
Section 2.1 Project Management Software Engineering Year 12 Assessment Task 2
# | Task / Activity | Stage | Person Responsible | Resources & Tools Required
1 | Client Meeting 1 to establish & document project requirements | Identifying & Defining | Adyan + Client | MS Teams, Meeting Minutes template
2 | Define & analyse problem requirements (context, needs, boundaries) |  | Adyan | MS Word, client notes
3 | Tools to develop ideas (implementation method analysis) |  |  | MS Word
4 | Project management (software development approach + Gantt chart) | Research & Planning |  | MS Word, MS Excel
5 | Quality assurance (quality criteria, compliance & legislation) |  |  | MS Word
6 | Data dictionary & data types
7 | Data flow diagrams (Level 0 & Level 1) |  |  | Apple Freeform
8 | Structure charts & class diagrams
9 | Storyboards (min. 6 screens)
10 | Decision trees & algorithm design (pseudocode)
11 | Client Meeting 2 to verify systems analysis & modelling |  | Adyan + Client | MS Teams, Meeting Minutes template
12 | Set up version control (create GitHub repository) | Producing & Implementing | Adyan | iCloud
13 | Develop software solution (code MRBS in Python) |  |  | Python 3, VS Code
14 | Capture screenshots & write implementation section |  |  | MS Word
15 | Test code (unit & black-box) + build test data tables | Testing & Evaluating |  | Python (VS Code), test data
16 | Gather user feedback (survey / observation) |  | Adyan + Client | Google Forms, MS Teams
17 | Evaluate code & solution against quality success criteria |  | Adyan | MS Word
18 | Client Meeting 3 to confirm solution meets requirements |  | Adyan + Client | MS Teams, Meeting Minutes template, Google Forms
19 | Compile, proofread & finalise full Systems Report |  | Adyan | MS Word